## Hookset Gantt
Hookset project daily Gantt chart
Edit Start date, Est. length (days), and % complete. End dates, status, daily bars, and overall task completion update automatically.
Overall task completion | 64.89% |  | Completed tasks | 57 |  |  |  |  | Done | Started | Not finished
 | time axis 2026-09-14 to 2026-11-08
Task | Description (optional) | Area | Est. length (days) | Start date | End date | Status | % complete | Progress basis | time axis 2026-09-14 to 2026-11-08
User entity | Map Users with a Long primary key, username, password hash, and administrator flag. | Entities | 1 | 2026-09-14 | 2026-09-14 | Done | 100% | Finished | 2026-09-14: 100%
Fly and material entities | Define fly, material, and size fields to match the MySQL tables. | Entities | 2 | 2026-09-15 | 2026-09-16 | Done | 100% | Finished | 2026-09-15: 100%; 2026-09-16: 100%
Fish entity | Map fish ID, FWP species ID, family, and species. | Entities | 1 | 2026-09-16 | 2026-09-16 | Done | 100% | Finished | 2026-09-16: 100%
Water-body entity | Map water-body IDs and names to the database. | Entities | 1 | 2026-09-17 | 2026-09-17 | Done | 100% | Finished | 2026-09-17: 100%
Long IDs and foreign keys | Update primary keys to BIGINT and Java Long and keep related foreign keys consistent. | Entities | 1 | 2026-09-18 | 2026-09-18 | Done | 100% | Finished | 2026-09-18: 100%
User repositories | Provide username lookup for signup and authentication. | Repositories | 1 | 2026-09-21 | 2026-09-21 | Done | 100% | Finished | 2026-09-21: 100%
Signup form and validation | Collect username, password, and confirmation and reject invalid or duplicate signup requests. | Services | 2 | 2026-09-21 | 2026-09-22 | Done | 100% | Finished | 2026-09-21: 100%; 2026-09-22: 100%
Security configuration | Configure public routes, protected routes, custom form login, and logout. | Security | 2 | 2026-09-21 | 2026-09-22 | Done | 100% | Finished | 2026-09-21: 100%; 2026-09-22: 100%
Home controller | Route GET / to the home page. | Controllers | 1 | 2026-09-21 | 2026-09-21 | Done | 100% | Finished | 2026-09-21: 100%
Shared Thymeleaf layout | Create reusable title and content fragments with a common header and footer. | Pages | 2 | 2026-09-21 | 2026-09-22 | Done | 100% | Finished | 2026-09-21: 100%; 2026-09-22: 100%
Bootstrap and Hookset theme | Add Bootstrap, green/sage/cream/gold colors, custom buttons, and the site stylesheet. | Styling | 3 | 2026-09-21 | 2026-09-23 | Done | 100% | Finished | 2026-09-21: 100%; 2026-09-22: 100%; 2026-09-23: 100%
Fish and water-body repositories | Add JPA repositories for retrieving fish and water bodies. | Repositories | 1 | 2026-09-22 | 2026-09-22 | Done | 100% | Finished | 2026-09-22: 100%
Signup service | Create the user account and encode the password with BCrypt. | Services | 2 | 2026-09-22 | 2026-09-23 | Done | 100% | Finished | 2026-09-22: 100%; 2026-09-23: 100%
Session management | Configure IF_REQUIRED sessions for authenticated users. | Security | 1 | 2026-09-22 | 2026-09-22 | Done | 100% | Finished | 2026-09-22: 100%
Login controller | Render the custom login page and supply its form model. | Controllers | 1 | 2026-09-22 | 2026-09-22 | Done | 100% | Finished | 2026-09-22: 100%
Home page | Create the initial Hookset landing page within the shared layout. | Pages | 1 | 2026-09-22 | 2026-09-22 | Done | 100% | Finished | 2026-09-22: 100%
Navigation and logo | Style the header, align navigation links, and use the transparent Hookset logo. | Styling | 1 | 2026-09-22 | 2026-09-22 | Done | 100% | Finished | 2026-09-22: 100%
Login service and user details | Load users for Spring Security and expose password hashes and USER or ADMIN authorities. | Services | 2 | 2026-09-23 | 2026-09-24 | Done | 100% | Finished | 2026-09-23: 100%; 2026-09-24: 100%
Signup controller | Handle GET and POST signup, display validation errors, and redirect successful signup to login. | Controllers | 1 | 2026-09-23 | 2026-09-23 | Done | 100% | Finished | 2026-09-23: 100%
Login page | Build the login form, card layout, and authentication alerts. | Pages | 1 | 2026-09-23 | 2026-09-23 | Done | 100% | Finished | 2026-09-23: 100%
Signup page | Build signup fields, validation messages, and success feedback. | Pages | 1 | 2026-09-24 | 2026-09-24 | Done | 100% | Finished | 2026-09-24: 100%
Water-body detail fields | Add type, state, description, and slug fields for water-body detail pages. | Entities | 1 | 2026-09-28 | 2026-09-28 | Done | 100% | Finished | 2026-09-28: 100%
Water-body DTO and mapper | Transfer water-body display fields between the entity and DTO, including descriptions and slugs. | Services | 1 | 2026-09-28 | 2026-09-28 | Done | 100% | Finished | 2026-09-28: 100%
Water-body list and detail routes | Supply the list model and retrieve a selected water body for its detail page. | Controllers | 1 | 2026-09-28 | 2026-09-28 | Done | 100% | Finished | 2026-09-28: 100%
Water-body list page | Display available waters as cards with links to their detail pages. | Pages | 2 | 2026-09-28 | 2026-09-29 | Done | 100% | Finished | 2026-09-28: 100%; 2026-09-29: 100%
Water-type illustrations | Prepare river, lake, and stream images for the water-body interface. | Styling | 1 | 2026-09-28 | 2026-09-28 | Done | 100% | Finished | 2026-09-28: 100%
Water-body and fish display services | Retrieve waters and their associated fish for page display through service interfaces. | Services | 2 | 2026-09-29 | 2026-09-30 | Done | 100% | Finished | 2026-09-29: 100%; 2026-09-30: 100%
Water-body detail page | Display the name, state, description, and related fish. | Pages | 2 | 2026-09-29 | 2026-09-30 | Done | 100% | Finished | 2026-09-29: 100%; 2026-09-30: 100%
Card and detail-page polish | Finish centered buttons, description widths, card alignment, and responsive spacing. Progress estimate; adjust as needed. | Styling | 2 | 2026-09-29 | 2026-09-30 | Done | 100% | Finished | 2026-09-29: 100%; 2026-09-30: 100%
Logging configuration and fix | Add console/rolling-file logging | Configuration | 2 | 2026-10-01 | 2026-10-02 | Done | 100% | Finished | 2026-10-01: 100%; 2026-10-02: 100%
Service/controller logging and Javadocs | Add logging messages and update Javadocs in the New fly/catch service log comments still need implementation. | Documentation | 2 | 2026-10-01 | 2026-10-02 | Done | 100% | Code reviewed | 2026-10-01: 100%; 2026-10-02: 100%
Profile form and validation | Add profile fields, password confirmation, and validation for account changes. | Forms | 1 | 2026-10-05 | 2026-10-05 | Done | 100% | Finished | 2026-10-05: 100%
Profile password-change service | Find the authenticated user, reject mismatched passwords or anonymous access, BCrypt-encode the new password, and save it. | Services | 2 | 2026-10-05 | 2026-10-06 | Done | 100% | Finished | 2026-10-05: 100%; 2026-10-06: 100%
Profile page and feedback | Create the profile page with account details, password fields, validation messages, and Hookset styling. | Pages | 2 | 2026-10-06 | 2026-10-07 | Done | 100% | Finished | 2026-10-06: 100%; 2026-10-07: 100%
Profile GET and POST controller | Populate the profile form with the logged-in username. Validate submissions and return errors or redirect after a password change. | Controllers | 1 | 2026-10-07 | 2026-10-07 | Done | 100% | Finished | 2026-10-07: 100%
Fly entity display fields | Update fly fields for catalog display, shared emblem filenames, size ranges, and slug-based detail links. | Entities | 1 | 2026-10-07 | 2026-10-07 | Done | 100% | Finished | 2026-10-07: 100%
Fly DTO and display mapper | Transfer fly ID, owner ID, name, type, color, size range, image, and slug from entities to display DTOs. | DTOs / mappers | 1 | 2026-10-07 | 2026-10-07 | Done | 100% | Finished | 2026-10-07: 100%
Fly catalog and user repositories | Query default flies with no owner, current-user flies, both groups together, and a selected fly by slug. | Repositories | 1 | 2026-10-07 | 2026-10-07 | Done | 100% | Finished | 2026-10-07: 100%
Fly GET services and current user | Implement default, mine, and all fly retrieval. Read the current user ID from HooksetUserDetails and map repository results. | Services | 2 | 2026-10-07 | 2026-10-08 | Done | 100% | Finished | 2026-10-07: 100%; 2026-10-08: 100%
Fly list page and filters | Build the responsive fly catalog table, emblem/name/type columns, filter links, and links to individual flies. | Pages | 2 | 2026-10-07 | 2026-10-08 | Done | 100% | Finished | 2026-10-07: 100%; 2026-10-08: 100%
Fly emblems and styling | Add dry, nymph, and streamer emblems and style fly images, gold borders, tables, detail content, and secondary buttons. | Styling | 2 | 2026-10-07 | 2026-10-08 | Done | 100% | Finished | 2026-10-07: 100%; 2026-10-08: 100%
Catch GET services | Retrieve all catches, current-user catches, and a selected catch by ID. Resolve related fish, fly, and water-body records. | Services | 2 | 2026-10-07 | 2026-10-08 | Done | 100% | Finished | 2026-10-07: 100%; 2026-10-08: 100%
All catches and my catches pages | Create separate catch tables showing fish species, water body, date, and links for catch details. | Pages | 2 | 2026-10-07 | 2026-10-08 | Done | 100% | Finished | 2026-10-07: 100%; 2026-10-08: 100%
Fly add form and GET page | Build the FlyForm and add-fly page with name, type, color, and size inputs. Include the "Add Fly" action in the "mine" view. | Forms / pages | 2 | 2026-10-07 | 2026-10-08 | Done | 100% | Finished | 2026-10-07: 100%; 2026-10-08: 100%
Fly list and detail GET routes | Handle /flies with hookset, mine, and all filters and /flies/details/{slug}. Supply fly and filter model attributes. | Controllers | 1 | 2026-10-08 | 2026-10-08 | Done | 100% | Finished | 2026-10-08: 100%
Fly detail page | Display the selected fly, emblem, type, color, size range, and return navigation. | Pages | 1 | 2026-10-08 | 2026-10-08 | Done | 100% | Finished | 2026-10-08: 100%
Fly DataTables JavaScript | Initialize DataTables with 20 rows per page, page-size options, name sorting, column widths, and unsortable emblem/action columns. | JavaScript | 1 | 2026-10-08 | 2026-10-08 | Done | 100% | Finished | 2026-10-08: 100%
Default fly catalog seed script | Prepare the 200-fly SQL catalog with Dry, Nymph, and Streamer records, example sizes, and shared image filenames. Script preparation is complete; execution is not verified. | Database | 1 | 2026-10-08 | 2026-10-08 | Done | 100% | Finished | 2026-10-08: 100%
Catch entity and display DTO | Define catch/user/fly/fish/water IDs, fish length, catch date/time, and notes. Include related display objects in CatchDto. | Entities / DTOs | 1 | 2026-10-08 | 2026-10-08 | Done | 100% | Finished | 2026-10-08: 100%
Catch repository and user lookup | Provide all-catch retrieval and findByUserId(Long) for the logged-in user. | Repositories | 1 | 2026-10-08 | 2026-10-08 | Done | 100% | Finished | 2026-10-08: 100%
Catch mapper and related DTOs | Map catch fields plus fish and water-body DTOs. Fly DTO is passed to the mapper but is not assigned in the reviewed commit; finish and verify the mapping. | DTOs / mappers | 2 | 2026-10-08 | 2026-10-09 | Started | 75% | Finished | 2026-10-08: 75%; 2026-10-09: 75%
Catch all and mine GET routes | Implement GET /catches and /catches/mine and populate the catches model for each template. | Controllers | 1 | 2026-10-08 | 2026-10-08 | Done | 100% | Finished | 2026-10-08: 100%
Catch DataTables JavaScript | Add 20-row pagination, page-size options, descending date sort, and fixed column-width proportions for catch tables. | JavaScript | 1 | 2026-10-08 | 2026-10-08 | Done | 100% | Finished | 2026-10-08: 100%
Authenticated navigation updates | Add Flies and Catches links when a user is signed in and include fly/catch scripts through the shared layout. | Pages / security | 1 | 2026-10-08 | 2026-10-08 | Done | 100% | Finished | 2026-10-08: 100%
Public fish and water-body access | Permit unauthenticated browsing of fish and water-body routes while retaining authentication for user features. | Security | 1 | 2026-10-08 | 2026-10-08 | Done | 100% | Finished | 2026-10-08: 100%
Fly add mapper, service, and POST | Map the add form to a Fly, set the current user ID, generate a slug, and save. POST submission was discussed tonight; final successful save is not verified. | Services / controllers | 2 | 2026-10-08 | 2026-10-09 | Done | 100% | Finished | 2026-10-08: 100%; 2026-10-09: 100%
Fly input and size-range validation | Add required inputs and size bounds. Resolve null numeric binding and sizeRangeValid getter errors and display useful feedback. | Forms | 2 | 2026-10-08 | 2026-10-09 | Done | 100% | Finished | 2026-10-08: 100%; 2026-10-09: 100%
Fly slug-generation debugging | Correct slug generation to use the fly name rather than an unset slug and handle the null trim error. Verify the add flow after the change. | Services | 1 | 2026-10-08 | 2026-10-08 | Done | 100% | Finished | 2026-10-08: 100%
Catch Service add, edit, delete catches | Implement logic to add user catches, edit, delete and validate user form entries | Services | 2 | 2026-10-09 | 2026-10-10 | Not finished | 0% | Planned | bar: 2026-10-09 to 2026-10-10
Create Posts in Catch Controller | Allow users to hit post endpoints for entering catches | Controllers | 1 | 2026-10-10 | 2026-10-10 | Not finished | 0% | Planned | bar: 2026-10-10
Create forms for catches | Create forms to add and edit a user catch | Pages | 1 | 2026-10-10 | 2026-10-10 | Not finished | 0% | Planned | bar: 2026-10-10
User and authentication models | Test User and HooksetUserDetails fields and USER/ADMIN authority behavior. | Unit testing | 1 | 2026-10-10 | 2026-10-10 | Not finished | 0% | Planned | bar: 2026-09-14 to 2026-11-08
Add Edit form for Flies | Create edit form, validate in service, post to controller | Pages | 1 | 2026-10-10 | 2026-10-10 | Not finished | 0% | Planned | bar: 2026-09-14 to 2026-11-08
Fish and water-body models | Test DTO/entity fields, Long IDs, descriptions, and slugs. | Unit testing | 1 | 2026-10-12 | 2026-10-12 | Not finished | 0% | Planned | bar: 2026-09-14 to 2026-11-08
DTO mappers | Verify every mapped field and null handling for fish and water-body conversions. | Unit testing | 1 | 2026-10-13 | 2026-10-13 | Not finished | 0% | Planned | bar: 2026-10-13
Signup service | Mock the repository and encoder. Test successful creation, duplicate usernames, and invalid inputs. | Unit testing | 2 | 2026-10-14 | 2026-10-15 | Not finished | 0% | Planned | bar: 2026-09-14 to 2026-11-08
Login service and user details | Test found and missing usernames, password-hash, and administrator roles. | Unit testing | 2 | 2026-10-15 | 2026-10-16 | Not finished | 0% | Planned | bar: 2026-10-15 to 2026-10-16
Water-body and fish services | Mock repositories. Test list retrieval, selected-water retrieval, related fish, and missing results. | Unit testing | 2 | 2026-10-17 | 2026-10-18 | Not finished | 0% | Planned | bar: 2026-09-14 to 2026-11-08
Login, logout, and sessions | Test public/protected routes, authentication success/failure, roles, CSRF, and session/logout behavior. Uses Spring test support. | Security testing | 3 | 2026-10-17 | 2026-10-19 | Not finished | 0% | Planned | bar: 2026-10-17 to 2026-10-19
Home and login controllers | Use controller-slice tests to verify routes, template names, and form model attributes. | Unit testing | 1 | 2026-10-18 | 2026-10-18 | Not finished | 0% | Planned | bar: 2026-09-14 to 2026-11-08
Signup controller | Test valid and invalid form submissions, duplicate feedback, redirects, and flash messages. | Unit testing | 2 | 2026-10-19 | 2026-10-20 | Not finished | 0% | Planned | bar: 2026-10-19 to 2026-10-20
Water-body controllers | Test list/detail models, slug routing, missing waters, and response behavior. | Unit testing | 2 | 2026-10-20 | 2026-10-21 | Not finished | 0% | Planned | bar: 2026-09-14 to 2026-11-08
Profile service unit tests | Test matching/mismatched passwords, missing users, anonymous access, BCrypt encoding, and repository saves. | Unit testing | 2 | 2026-10-21 | 2026-10-22 | Not finished | 0% | Planned | bar: 2026-10-21 to 2026-10-22
Fly add service unit tests | Test form-to-entity mapping, ownership, save behavior, valid names, null names, slug generation, and duplicate slug behavior. | Unit testing | 3 | 2026-10-21 | 2026-10-23 | Not finished | 0% | Planned | bar: 2026-09-14 to 2026-11-08
Catch GET service unit tests | Test all/mine/ID retrieval, current-user lookup, empty results, missing catches, related-record lookups, and DTO contents. | Unit testing | 3 | 2026-10-21 | 2026-10-23 | Not finished | 0% | Planned | bar: 2026-10-21 to 2026-10-23
Profile controller and form tests | Test GET model fields, validation failures, failed password changes, redirects, and password-confirmation rules. | Unit testing | 2 | 2026-10-22 | 2026-10-23 | Not finished | 0% | Planned | bar: 2026-09-14 to 2026-11-08
Fly GET service unit tests | Mock repositories for hookset/mine/all filters, current-user IDs, empty results, DTO mapping, and found/missing slugs. | Unit testing | 2 | 2026-10-22 | 2026-10-23 | Not finished | 0% | Planned | bar: 2026-10-22 to 2026-10-23
Fly and catch mapper/model tests | Verify every display field, nested fish/fly/water DTO, date/length/notes field, and Long identifier. | Unit testing | 2 | 2026-10-22 | 2026-10-23 | Not finished | 0% | Planned | bar: 2026-09-14 to 2026-11-08
JPA repositories and mappings | Use repository integration tests for username lookups, persistence mappings, Long IDs, and fish/water associations. | Repository testing | 3 | 2026-10-24 | 2026-10-26 | Not finished | 0% | Planned | bar: 2026-10-24 to 2026-10-26
Thymeleaf forms and layout | Verify rendered layout, login/signup errors, success alerts, form actions, and navigation links. Rendering tests supplement units. | Page testing | 2 | 2026-10-24 | 2026-10-25 | Not finished | 0% | Planned | bar: 2026-09-14 to 2026-11-08
Responsive styling | Check cards, buttons, image sizing, text widths, and header/footer at mobile and desktop widths. Visual checks supplement units. | UI testing | 2 | 2026-10-24 | 2026-10-25 | Not finished | 0% | Planned | bar: 2026-10-24 to 2026-10-25
Fly controller and form tests | Test catalog filter defaults, detail models, add GET/POST, invalid inputs, blank numeric values, and minimum/maximum size rules. | Unit testing | 3 | 2026-10-24 | 2026-10-26 | Not finished | 0% | Planned | bar: 2026-09-14 to 2026-11-08
Fly, catch, and profile page checks | Check rendered fields, forms, links, filters, ownership display, validation feedback, responsive layouts, and DataTables pagination/sorting. | Page / UI testing | 3 | 2026-10-24 | 2026-10-26 | Not finished | 0% | Planned | bar: 2026-10-24 to 2026-10-26
Public routes and navigation tests | Verify public fish/water access, protected user pages, signed-in navigation, CSRF, and authentication-sensitive catalog behavior. | Security testing | 2 | 2026-10-24 | 2026-10-25 | Not finished | 0% | Planned | bar: 2026-09-14 to 2026-11-08
Logging configuration checks | Verify startup with the rolling policy and demonstrate enabling/disabling logging for an individual class. | Configuration testing | 1 | 2026-10-24 | 2026-10-24 | Not finished | 0% | Planned | bar: 2026-10-24
Water-body pages | Verify rendered list/detail content, images, descriptions, fish display, and links. | Page testing | 1 | 2026-10-25 | 2026-10-25 | Not finished | 0% | Planned | bar: 2026-09-14 to 2026-11-08
Catch controller tests | Test all/mine model contents and templates, authentication behavior, and the detail route once implemented. | Unit testing | 2 | 2026-10-25 | 2026-10-26 | Not finished | 0% | Planned | bar: 2026-10-25 to 2026-10-26
Fly and catch repository tests | Verify default/custom fly queries, slug lookup, current-user catch filtering, and persistence mappings against test data. | Repository testing | 3 | 2026-10-25 | 2026-10-27 | Not finished | 0% | Planned | bar: 2026-09-14 to 2026-11-08
Fix failures and rerun suite | Resolve test failures and run the complete scoped test suite before final review. | Testing | 4 | 2026-10-31 | 2026-11-03 | Not finished | 0% | Planned | bar: 2026-10-31 to 2026-11-03