## Hookset Gantt
Hookset project Gantt chart
Progress as of October 1, 2026. Historical weeks reconstructed from project discussions; testing dates are proposed.
Edit Start date and % complete. End dates, status, weekly bars, and overall progress update automatically. Enter percentages as 50%.
Every task is scheduled for one Monday–Sunday week. Parallel rows share a week. Descriptions are optional editable text.
Scope: entities, repositories, services, controllers, pages, styling, and testing. Importers and API calls excluded.
Overall task completion | 65.34% |  | Completed tasks | 28 |  |  |  |  | Done: 100% | Started: 1–99% | Not finished: 0%
[9 empty] | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02
Task | Area | Length (weeks) | Start date | End date | Status | % complete | Description (optional) | Progress basis | 2026-09-20 | 2026-09-27 | 2026-10-04 | 2026-10-11 | 2026-10-18 | 2026-10-25 | 2026-11-01 | 2026-11-08
User entity | Entities | 1 | 2026-09-14 | 2026-09-20 | Done | 100% | Map Users with a Long primary key, username, password hash, and administrator flag. | Complete | 2026-09-20: 100%
Fly and material entities | Entities | 1 | 2026-09-14 | 2026-09-20 | Done | 100% | Define fly, material, and size fields to match the MySQL tables. | Complete | 2026-09-20: 100%
Fish entity | Entities | 1 | 2026-09-14 | 2026-09-20 | Done | 100% | Map fish ID, Family, and species. | Complete | 2026-09-20: 100%
Water-body entity | Entities | 1 | 2026-09-14 | 2026-09-20 | Done | 100% | Map water-body IDs and names to the database. | Complete | 2026-09-20: 100%
Long IDs and foreign keys | Entities | 1 | 2026-09-14 | 2026-09-20 | Done | 100% | Update primary keys to BIGINT and Java Long and keep related foreign keys consistent. | Complete | 2026-09-20: 100%
User repositories | Repositories | 1 | 2026-09-21 | 2026-09-27 | Done | 100% | Provide username lookup for signup and authentication. | Complete | 2026-09-27: 100%
Fish and water-body repositories | Repositories | 1 | 2026-09-21 | 2026-09-27 | Done | 100% | Add JPA repositories for retrieving fish and water bodies. | Complete | 2026-09-27: 100%
Signup form and validation | Services | 1 | 2026-09-21 | 2026-09-27 | Done | 100% | Collect username, password, and confirmation and reject invalid or duplicate signup requests. | Complete | 2026-09-27: 100%
Signup service | Services | 1 | 2026-09-21 | 2026-09-27 | Done | 100% | Create the user account and encode the password with BCrypt. | Complete | 2026-09-27: 100%
Login service and user details | Services | 1 | 2026-09-21 | 2026-09-27 | Done | 100% | Load users for Spring Security | Complete | 2026-09-27: 100%
Security configuration | Security | 1 | 2026-09-21 | 2026-09-27 | Done | 100% | Configure public routes, protected routes, custom form login | Complete | 2026-09-27: 100%
Session management | Security | 1 | 2026-09-21 | 2026-09-27 | Done | 100% | Configure IF_REQUIRED sessions for authenticated users. | Complete | 2026-09-27: 100%
Home controller | Controllers | 1 | 2026-09-21 | 2026-09-27 | Done | 100% | Route GET / to the home page. | Complete | 2026-09-27: 100%
Login controller | Controllers | 1 | 2026-09-21 | 2026-09-27 | Done | 100% | Render the custom login page and supply its form model. | Complete | 2026-09-27: 100%
Signup controller | Controllers | 1 | 2026-09-21 | 2026-09-27 | Done | 100% | Handle GET and POST signup, display validation errors, and redirect successful signup to login. | Complete | 2026-09-27: 100%
Shared Thymeleaf layout | Pages | 1 | 2026-09-21 | 2026-09-27 | Done | 100% | Create reusable title and content fragments with a common header and footer. | Complete | 2026-09-27: 100%
Home page | Pages | 1 | 2026-09-21 | 2026-09-27 | Done | 100% | Create the initial Hookset landing page within the shared layout. | Complete | 2026-09-27: 100%
Login page | Pages | 1 | 2026-09-21 | 2026-09-27 | Done | 100% | Build the login form, card layout, and authentication alerts. | Complete | 2026-09-27: 100%
Signup page | Pages | 1 | 2026-09-21 | 2026-09-27 | Done | 100% | Build signup fields, validation messages, and success feedback. | Complete | 2026-09-27: 100%
Bootstrap and Hookset theme | Styling | 1 | 2026-09-21 | 2026-09-27 | Done | 100% | Add Bootstrap, green/sage/cream/gold colors, custom buttons, and the site stylesheet. | Complete | 2026-09-27: 100%
Navigation and logo | Styling | 1 | 2026-09-21 | 2026-09-27 | Done | 100% | Style the header, align navigation links, and use the transparent Hookset logo. | Complete | 2026-09-27: 100%
Water-body detail fields | Entities | 1 | 2026-09-28 | 2026-10-04 | Done | 100% | Add type, state, description, and slug fields for water-body detail pages. | Complete | 2026-10-04: 100%
Water-body DTO and mapper | Services | 1 | 2026-09-28 | 2026-10-04 | Done | 100% | Transfer water-body display fields between the entity and DTO, including descriptions and slugs. | Complete | 2026-10-04: 100%
Water-body and fish display services | Services | 1 | 2026-09-28 | 2026-10-04 | Done | 100% | Retrieve waters and their associated fish for page display through service interfaces. | Complete | 2026-10-04: 100%
Water-body list and detail routes | Controllers | 1 | 2026-09-28 | 2026-10-04 | Done | 100% | Supply the list model and retrieve a selected water body for its detail page. | Complete | 2026-10-04: 100%
Water-body list page | Pages | 1 | 2026-09-28 | 2026-10-04 | Done | 100% | Display available waters as cards with links to their detail pages. | Complete | 2026-10-04: 100%
Water-body detail page | Pages | 1 | 2026-09-28 | 2026-10-04 | Done | 100% | Display the name, state, description, and related fish. | Complete | 2026-10-04: 100%
Water-type illustrations | Styling | 1 | 2026-09-28 | 2026-10-04 | Done | 100% | Prepare river, lake, and stream images for the water-body interface. | Complete | 2026-10-04: 100%
Card and detail-page polish | Styling | 1 | 2026-09-28 | 2026-10-04 | Started | 75% | Finish centered buttons, description widths, card alignment, and responsive spacing. Progress estimate; adjust as needed. | Complete | 2026-10-04: 100%
User and authentication models | Unit testing | 1 | 2026-10-05 | 2026-10-11 | Not finished | 0% | Test User and HooksetUserDetails fields and USER/ADMIN authority behavior. | Planned | bar: 2026-10-11
Fish and water-body models | Unit testing | 1 | 2026-10-05 | 2026-10-11 | Not finished | 0% | Test DTO/entity fields, Long IDs, descriptions, and slugs. | Planned | bar: 2026-10-11
DTO mappers | Unit testing | 1 | 2026-10-05 | 2026-10-11 | Not finished | 0% | Verify every mapped field and null handling for fish and water-body conversions. | Planned | bar: 2026-09-20 to 2026-11-08
Signup service | Unit testing | 1 | 2026-10-05 | 2026-10-11 | Not finished | 0% | Test successful creation, duplicate usernames, and invalid inputs. | Planned | bar: 2026-10-11
Login service and user details | Unit testing | 1 | 2026-10-05 | 2026-10-11 | Not finished | 0% | Test found and missing usernames, password-hash handoff, and administrator roles. | Planned | bar: 2026-09-20 to 2026-11-08
Water-body and fish services | Unit testing | 1 | 2026-10-12 | 2026-10-18 | Not finished | 0% | Test list retrieval, selected-water retrieval, related fish, and missing results. | Planned | bar: 2026-10-18
Home and login controllers | Unit testing | 1 | 2026-10-12 | 2026-10-18 | Not finished | 0% | Use controller-slice tests to verify routes, template names, and form model attributes. | Planned | bar: 2026-09-20 to 2026-11-08
Signup controller | Unit testing | 1 | 2026-10-12 | 2026-10-18 | Not finished | 0% | Test valid and invalid form submissions, duplicate feedback, redirects, and flash messages. | Planned | bar: 2026-10-18
Water-body controllers | Unit testing | 1 | 2026-10-12 | 2026-10-18 | Not finished | 0% | Test list/detail models, slug routing, missing waters, and response behavior. | Planned | bar: 2026-09-20 to 2026-11-08
Login, logout, and sessions | Security testing | 1 | 2026-10-12 | 2026-10-18 | Not finished | 0% | Test public/protected routes, authentication success/failure, roles, and session/logout behavior. Use Spring test support. | Planned | bar: 2026-10-18
JPA repositories and mappings | Repository testing | 1 | 2026-10-19 | 2026-10-25 | Not finished | 0% | Use repository integration tests for username lookups, persistence mappings, Long IDs, and fish/water associations. | Planned | bar: 2026-09-20 to 2026-11-08
Thymeleaf forms and layout | Page testing | 1 | 2026-10-19 | 2026-10-25 | Not finished | 0% | Verify rendered layout, login/signup errors, success alerts, form actions, and navigation links. Rendering tests supplement units. | Planned | bar: 2026-10-25
Water-body pages | Page testing | 1 | 2026-10-19 | 2026-10-25 | Not finished | 0% | Verify rendered list/detail content, images, descriptions, fish display, and links. | Planned | bar: 2026-09-20 to 2026-11-08
Responsive styling | UI testing | 1 | 2026-10-19 | 2026-10-25 | Not finished | 0% | Check cards, buttons, image sizing, text widths, and header/footer at mobile and desktop widths. Visual checks supplement units. | Planned | bar: 2026-10-25
Fix failures and rerun suite | Testing | 1 | 2026-10-26 | 2026-11-01 | Not finished | 0% | Resolve test failures and run the complete scoped test suite before final review. | Planned | bar: 2026-09-20 to 2026-11-08